## Gannt_11052025_11182025
Data
Work item | Name | Estimated Work | Remaining Work
24239 | Branding: Variablize font color for categories in option pricing | 31 | 1
28596 | Design Selections: Image disparity | 28 | 18
28613 | Auth: Migrate Spike code to development branch | 48.5 | 0
28614 | Auth: Implement domain match policy | 43 | 5
28615 | Auth: Okta user can authenticate to VDS | 24 | 24
28616 | Auth: display "user not provisioned" error message | 18 | 2
28645 | Interfacelift Training "3rd Party Authorization 2" | 45 | 43.5
28652 | RC for 11/10 | 0 | 0
28653 | Regression Test: Today's Appts | 0 | 3

## DirectQuery_11052025_11182025
Project: VeoDesignStudio Server: dev.azure.com/buildontechnologies Query: CurrentIterationTaskCapacity List type: Flat
ID | Work Item Type | Title | Tags | Remaining Work | Original Estimate | Activity | Parent
24239 | Product Backlog Item | Branding: Variablize font color for categories in option pricing | branding
28596 | Bug | Design Selections: Image disparity
28613 | Product Backlog Item | Auth: Migrate Spike code to development branch | Auth; scripts |  |  |  | 28426
28614 | Product Backlog Item | Auth: Implement domain match policy | Auth |  |  |  | 28426
28615 | Product Backlog Item | Auth: Okta user can authenticate to VDS | Auth |  |  |  | 28426
28616 | Product Backlog Item | Auth: display "user not provisioned" error message | Auth |  |  |  | 28426
28645 | Product Backlog Item | Interfacelift Training "3rd Party Authorization 2" | No QA
28646 | Task | Justin Training |  | 15 | 15 | Development | 28645
28647 | Task | Daniel Training |  | 15 | 15 | Development | 28645
28648 | Task | Reid Training |  | 13.5 | 15 | Development | 28645
28651 | Task | Write Test Cases |  | 3 |  | Test Design | 28653
28652 | Product Backlog Item | RC for 11/10
28653 | Product Backlog Item | Regression Test: Today's Appts | QA only |  |  |  | 21389
28654 | Task | Create and deploy RC |  |  |  | Development | 28652
28655 | Task | Test RC in Staging |  |  |  | Testing | 28652
28656 | Task | Run e2e automated test in Staging |  |  |  | Testing | 28652
28657 | Task | Deployment Planning Meeting |  |  |  |  | 28652
28658 | Task | Write QA Tests |  |  | 3 | Test Design | 28613
28659 | Task | Execute QA Tests |  |  | 4 | Testing | 28613
28660 | Task | PO Review |  |  | 1 |  | 28613
28661 | Task | Write QA Tests |  |  | 3 | Test Design | 28614
28662 | Task | Execute QA Tests |  | 4 | 4 | Testing | 28614
28663 | Task | PO Review |  | 1 | 1 |  | 28614
28664 | Task | Write QA Tests |  | 3 | 3 | Test Design | 28615
28665 | Task | Execute QA Tests |  | 4 | 4 | Testing | 28615
28666 | Task | PO Review |  | 1 | 1 |  | 28615
28667 | Task | Entity creation |  |  | 2 | Development | 28613
28668 | Task | Write QA Tests |  |  | 2 | Test Design | 28616
28669 | Task | Execute QA Tests |  | 1 | 1 | Testing | 28616
28670 | Task | Run migration |  |  | 2 | Development | 28613
28671 | Task | PO Review |  | 1 | 1 |  | 28616
28672 | Task | Confirmation Testing |  | 3 | 3 | Testing | 28596
28673 | Task | Update GetAuthProviders use case |  |  | 4 | Development | 28613
28674 | Task | PO Review |  | 1 | 1 |  | 28596
28675 | Task | Write QA Tests |  |  | 2 | Test Design | 24239
28676 | Task | PO Review |  | 1 | 1 |  | 24239
28677 | Task | Execute QA Tests |  |  | 3 | Testing | 24239
28679 | Task | Validate JWTs |  |  | 4 | Development | 28613
28680 | Task | Update the authenticate use case |  |  | 4 | Development | 28613
28681 | Task | Script auth providers |  |  | 1 | Development | 28613
28682 | Task | In the frontend, remove call to fetch all auth providers |  |  | 1 | Development | 28613
28683 | Task | PR |  |  | 3 | Development | 28613
28684 | Task | Update Postman collection for POST endpoint |  |  | 2 | Development | 28613
28685 | Task | Write unit tests |  |  | 8 | Development | 28613
28686 | Task | Developer Testing |  |  | 9 | Development | 28613
28687 | Task | Entity creation |  |  | 2 | Development | 28614
28688 | Task | Run migration |  |  | 2 | Development | 28614
28689 | Task | Create use case to fetch auth provider from email domain |  |  | 4 | Development | 28614
28690 | Task | New endpoint |  |  | 1 | Development | 28614
28691 | Task | Debounce logic on sign in screen and fetch providers |  |  | 5 | Development | 28614
28692 | Task | Unit tests for new use case |  |  | 4 | Development | 28614
28693 | Task | Update Postman collection |  |  | 2 | Development | 28614
28694 | Task | Make UI look good in any reasonable case |  |  | 3 | Development | 28614
28695 | Task | PR |  |  | 3 | Development | 28614
28696 | Task | Developer Testing |  |  | 9 | Development | 28614
28697 | Test Plan | 3rd Party Authorization 2
28698 | Test Suite | 3rd Party Authorization 2
28701 | Task | Developer Testing |  | 12 | 12 | Development | 28615
28702 | Task | Possible code changes |  | 4 | 4 | Development | 28615
28703 | Task | Throw specified error when necessary in use case |  |  | 2 | Development | 28616
28704 | Task | Respond to error in UI |  |  | 3 | Development | 28616
28705 | Task | PR |  |  | 3 | Development | 28616
28706 | Task | Developer Testing |  |  | 6 | Development | 28616
28707 | Task | Find the bug |  |  | 10 | Development | 28596
28708 | Task | Document to QA steps to eradicate bug |  | 2 | 2 | Development | 28596
28709 | Task | Exterminate da bug |  | 4 | 4 | Development | 28596
28710 | Task | PR |  | 2 | 2 | Development | 28596
28711 | Task | Developer Testing |  | 6 | 6 | Development | 28596
28712 | Task | Create new variable for option pricing menu text |  |  | 2 | Development | 24239
28713 | Task | Create new variable for DMH and DS if necessary |  |  | 6 | Development | 24239
28714 | Task | Map variables to palette slot |  |  | 2 | Development | 24239
28715 | Task | Document changes |  |  | 1 | Development | 24239
28716 | Task | PR |  |  | 3 | Development | 24239
28717 | Task | Developer Testing |  |  | 9 | Development | 24239
28718 | Task | Talk to Rob about Doofenshmirtz |  |  | 2 | Development | 24239
28736 | Task | Update Postman Collection for GET endpoint |  |  | 0.5 |  | 28613
28745 | Test Case | Branding: Variablize font color for categories in option pricing (Default theme)
28749 | Test Case | Branding: Variablize font color for categories in option pricing (Custom themes)
28750 | Test Case | Auth: Migrate Spike code to development branch
28751 | Test Case | Modify temporary password via VEO Admin
28849 | Test Suite | 24239 : Branding: Variablize font color for categories in option pricing
28850 | Test Suite | 28613 : Auth: Migrate Spike code to development branch
28851 | Test Suite | 28614 : Auth: Implement domain match policy
28852 | Test Suite | 28615 : Auth: Okta user can authenticate to VDS
28853 | Test Suite | 28616 : Auth: display "user not provisioned" error message

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | Deployment | \ | Deployment | Bug | Deployment
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | \Defects | Design | \Active | Design | Epic | Design
|  |  |  | \Integration | Development | \Active\Product Backlog | Development | Feature | Development
|  |  |  | \Product Team | Documentation | \Active\Product Backlog\3rd Party Authorization 1 | Documentation | Impediment | Documentation
|  |  |  | \Product Team\Story Time | Requirements | \Active\Product Backlog\3rd Party Authorization 2 | Requirements | Initiative | Requirements
|  |  |  | \Requests | Testing | \Active\Product Backlog\Assigned Communities 1 | Test Design | Product Backlog Item | Testing
|  |  |  | all_VSTS_3e70086c_f553_49d1_81be_7ca3114b6431_System.AreaPath | all_VSTS_3e70086c_f553_49d1_81be_7ca3114b6431_Bug_Microsoft.VSTS.Common.Activity | \Active\Product Backlog\Assigned Communities 2 | Testing | Task | Test Design
[6 empty] | \Active\Product Backlog\Branding - Flintrock | all_VSTS_3e70086c_f553_49d1_81be_7ca3114b6431_Task_Microsoft.VSTS.Common.Activity | Test Case | all_VSTS_3e70086c_f553_49d1_81be_7ca3114b6431_Microsoft.VSTS.Common.Activity
[6 empty] | \Active\Product Backlog\Branding Theme Editor 1 |  | all_VSTS_3e70086c_f553_49d1_81be_7ca3114b6431_System.WorkItemType
\Active\Product Backlog\Branding Theme Editor 2
\Active\Product Backlog\Branding Theme Editor 4
\Active\Product Backlog\Branding Theme Editor 5
\Active\Product Backlog\Branding Theme Editor 6
\Active\Product Backlog\Branding Theme Editor 7
\Active\Product Backlog\Branding Theme Version 3
\Active\Product Backlog\Builder Branding - Foundation 1
\Active\Product Backlog\Builder Branding - Foundation 2
\Active\Product Backlog\Builder Branding 3
\Active\Product Backlog\Builder Branding 4
\Active\Product Backlog\Builder Option Codes 1
\Active\Product Backlog\Builder Option Codes 2
\Active\Product Backlog\Buyer Dashboard Improvements 1
\Active\Product Backlog\Buyer Dashboard Improvements 2
\Active\Product Backlog\Catalog Documents 1
\Active\Product Backlog\Catalog Documents 2
\Active\Product Backlog\Enhanced Categories 1
\Active\Product Backlog\Front End Framework 1
\Active\Product Backlog\Front End Framework 2
\Active\Product Backlog\Front-End Framework Focus Sprint 1
\Active\Product Backlog\Front-End Framework Focus Sprint 2
\Active\Product Backlog\Lifestyle Survey 1
\Active\Product Backlog\Lifestyle Survey 2
\Active\Product Backlog\Manage Designers
\Active\Product Backlog\Misc Work July 2024-1
\Active\Product Backlog\Misc Work June 2024-1
\Active\Product Backlog\Misc Work June 2024-2
\Active\Product Backlog\Misc Work March 2024
\Active\Product Backlog\Misc Work Nov-2024-A
\Active\Product Backlog\Misc Work Oct-2024-A
\Active\Product Backlog\Misc Work Oct-2024-B
\Active\Product Backlog\VDS Sprint 11 Feb
\Active\Product Backlog\VDS Sprint 11 Mar
\Active\Product Backlog\VDS Sprint 14 Jan
\Active\Product Backlog\VDS Sprint 17 Dec
\Active\Product Backlog\VDS Sprint 19 Nov
\Active\Product Backlog\VDS Sprint 25 Feb
\Active\Product Backlog\VDS Sprint 25 Mar
\Active\Product Backlog\VDS Sprint 28 Jan
\Active\Product Backlog\VDS Sprint 3 Dec
\Active\Product Backlog\Virtual Model Home 1
\Active\Product Backlog\Virtual Model Home 2
\Active\Product Backlog\Visualize Packages 1
\Active\Product Backlog\Visualize Packages 2
\Active\Product Backlog\Visualize Packages 3
\Active\Product Backlog\Visualize Packages 4
\Active\Product Backlog\Visualize Packages 5
\Active\Product Backlog\Visualize Packages 6
\Active\Product Backlog\Work Nov-2024-B
\Active\Product Backlog\Work-Dec-2024-A
\Active\Product Backlog\Work-Last 2024-First 2025
\Archive
\Archive\Collections
\Archive\Collections\Collections - Increment 1
\Archive\Collections\Collections - Increment 1\Collections Sprint 0
\Archive\Collections\Collections - Increment 1\Collections Sprint 0.2
\Archive\Collections\Collections - Increment 2
\Archive\Integrations
\Archive\Integrations\Ravenna
\Archive\Integrations\Ravenna\Report Integration
\Archive\Integrations\Taylor Morrison
\Archive\Integrations\Taylor Morrison\Catalog Manipulation
\Archive\Permissions
\Archive\Permissions\DMH Improvements 2
\Archive\Permissions\DMH Improvements 3
\Archive\Permissions\Permissions 1
\Archive\Permissions\Permissions 2
\Archive\Permissions\Permissions 3
\Archive\Permissions\Permissions 4
\Archive\Permissions\VeoSolutions 1
\Archive\Permissions\VeoSolutions 2
\Archive\Permissions\VeoSolutions 3
\Archive\Permissions\VeoSolutions 4
\Archive\Permissions\Veosolutions 5
\Archive\Permissions\VeoSolutions 6
\Archive\PO Work January 2
\Archive\Product Backlog
\Archive\Product Backlog\2023 Sprint 1
\Archive\Product Backlog\Appointment Confirmation
\Archive\Product Backlog\Bug Fixes and Cleanup
\Archive\Product Backlog\Bug Fixes and Cleanup 2
\Archive\Product Backlog\Edit Quantity 1
\Archive\Product Backlog\Edit Quantity 2
\Archive\Product Backlog\Edit Quantity 3
\Archive\Product Backlog\Embedded Visualizer 1
\Archive\Product Backlog\Embedded Visualizer 2
\Archive\Product Backlog\End of Year Sprint 2022
\Archive\Product Backlog\Lay Direction
\Archive\Product Backlog\Misc Work - Sept 2023
\Archive\Product Backlog\Misc Work December 2023 (sprint 1)
\Archive\Product Backlog\Misc Work December 2023 (sprint 2)
\Archive\Product Backlog\Misc Work November 2023 (sprint 1)
\Archive\Product Backlog\Misc Work November 2023 (sprint 2)
\Archive\Product Backlog\Misc Work Oct 2022
\Archive\Product Backlog\Option Pricing (no pricing) 2
\Archive\Product Backlog\Option Pricing (no pricing) 3
\Archive\Product Backlog\Option Pricing No Pricing 1
\Archive\Product Backlog\Scheduler 1
\Archive\Product Backlog\Scheduler 2
\Archive\Product Backlog\Scheduler 3
\Archive\Product Backlog\Sub Area Selections 1
\Archive\Product Backlog\Sub Area Selections 2
\Archive\Product Backlog\Sub Area Selections 3
\Archive\Product Backlog\Sub Area Selections 4
\Archive\Product Backlog\Sub Area Selections 5
\Archive\Product Backlog\TM 1
\Archive\Product Backlog\VCMS 1
\Archive\Product Backlog\VCMS 2
\Archive\Product Backlog\VCMS 3
\Archive\Product Backlog\VCMS 4
\Archive\Product Backlog\VCMS 5
\Archive\Product Backlog\VCMS Research
\Archive\Product Backlog\Vis Programs 2
\Archive\Product Backlog\Vis Programs 3
\Archive\Product Backlog\Vis Programs 4
\Archive\Product Backlog\Vis Programs 5
\Archive\Product Backlog\Vis Programs 6
\Archive\Product Backlog\Vis Programs 7
\Archive\Product Backlog\Visualization Programs
\Archive\Product Backlog\Visualize Catalog 1
\Archive\Product Backlog\Visualize Catalog 2
\Archive\Product Backlog\Visualize Catalog 3
\Archive\Product Backlog\VSP - 2
\Archive\Product Backlog\VSP - 3
\Archive\Product Backlog\VSP - 4
\Archive\Product Backlog\VSP - Designer Docs
\Archive\Product Backlog\Wrap up - Vis Catalog and Appt Confirmation
\Archive\Product Sprint - April 12
\Archive\Product Sprint 10
\Archive\Product Team 12
\Product Owner
\Product Owner\DMH Improvements
\Product Owner\Product Sprint - March 29
\Product Owner\Product Sprint 9
\Product Owner\Ready To Score
all_VSTS_3e70086c_f553_49d1_81be_7ca3114b6431_System.IterationPath